## Timeline
| Updated Date: | 2026-07-14
No | Description | Day(s) | Start Date | End Date | Completion % | Status | Remark
1 | Payment Milestone 1. Upon Confirmation | x |  | TBC | TBC | TBC
2 | UI/UX Mockups | 13 | 2026-07-08 | 2026-07-20 | 53.8462 | In Progress | 8/7/2026 - First draft has been sent out - Eddie has commented accordingly
3 | Frontend Development - Phase 3a - Phase 3b | 3 | 2026-07-20 | 2026-07-22 | 0 | Pending
4 | Backend Development - Phase 3a - Phase 3b | 3 | 2026-07-20 | 2026-07-22 | 0 | Pending
5 | UAT (User Acceptance Testing) | 2 | 2026-07-22 | 2026-07-23 | 0 | Pending
6 | Go Live | 1 | 2026-07-24 | 2026-07-24 | 0 | Pending
7 | Payment Milestone 1. Completion | x |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC
|  |  |  | TBC | TBC | TBC

## P1 - Foundation - OLD (hidden)
No | Phase | Name | Location (How to access) | Design (Pending) | Information (Member Page) - Member View | Information (Back Office) - Admin View | Filters | Api Name in Documentation
1 | 1 | Member List | Side Bar Title - Member List | Wireframe | - | Member List (All Member) Details here: [G6] MRS - Project Details - Phase 2 | Details here: [G6] MRS - Project Details - Phase 2
2 | 1 | Token Log | Member Page 1. Member profile Back Office 1. Member List 2. Report | Wireframe | Token History 1. Date/time 2. Category - Welcome gift - Check In - Luckyspin - Profile details - Deposit 3. Token details 4. Amount +/- | Member List (Each Member) 1. Date/time 2. Category - Welcome gift - Check In - Luckyspin - Profile details - Deposit 3. Token details 4. Amount +/- Report (All Member's) 1. Phone number 2. Username 3. Station 4. Date/time 5. Category - Welcome gift - Check In - Luckyspin - Profile details - Deposit 6. Token details 7. Amount +/- | Filter by Member List (Each Member) Date/Time Category Token Details Report (All Member) Date/Time Category Token Details Username Phone Number Station
3 | 1 | Reward Log | Member Page 1. Member profile Back Office 1. Member List 2. Report | Wireframe | Reward History 1. Date/time 2. Category - Luckyspin - Redemption Mart - VIP 3. Reward details - Bonus - Prize - Redemption items 4. Reward name | Member List (Each Member) 1. Date/time 2. Category - Luckyspin - Redemption Mart - VIP 3. Reward details - Bonus - Prize - Redemption items 4. Reward name Report (All Member's) 1. Phone number 2. Username 3. Station 4. Date/time 5. Category - Luckyspin - Redemption Mart - VIP 6. Reward details - Bonus - Prize - Redemption items 7. Reward name | Filter by Member List (Each Member) Date/Time Category Reward Details Reward Name Report (All Member) Date/Time Category Reward Details Reward Name Username Phone Number Station
4 | 1 | Deposit Log | Back Office 1. Member List | Wireframe | - | Member List (Each Member) 1. Date/time 2. Station 3. Amount | Filter by Date/Time Station
5 | 1 | Member Report | Back Office Report - Member Report | Wireframe | - | Member Report Show by Daily, Monthly, Yearly 1. New Member 2. Total Member 3. Active member 4. Token Issued | from_date / to_date
6 | 1 | Home Dashboard | First Page upon logging in | Total Users - One Number Daily Check in - Bar Graph Active Users Today - Pie Chart |  | Total Users Daily Check in Summary Active Users Today

## Prediction (hidden)
Module | Description
System Name | World Cup Prediction Game
Purpose | User predicts World Cup match winners
Prediction Type | Win / Lose Only (No Draw)
Match Source | Admin manually creates matches
Result Source | Admin manually updates winning team
Update Mode | After match ends
RULES（规则系统）
Rule | Description
Participation Requirement | Current Month Total Deposit ≥ RM300
Deposit Requirement | RM300 is eligibility requirement only (not deducted)
Prediction Limit | 1 prediction per user per match
Prediction Change | Not allowed after submission
Match Start | Prediction automatically closes when match starts
Win Rule | User can continue participating without any additional requirement
Lose Rule | User must deposit RM50 to unlock next prediction
Repeated Loss | Every loss requires a new RM50 deposit to continue
Result Logic | Selected winning team = WIN
Result Logic | Selected losing team = LOSE
MATCH MANAGEMENT（赛事管理）
Item | Rule
Match Creation | Admin manually creates Team A vs Team B
Match Status | Upcoming / Closed / Settled
Match Settlement | Admin manually selects winning team
Auto Settlement | System marks WIN / LOSE based on selected winner
ELIGIBILITY CHECK（参与资格）
Item | Rule
Initial Eligibility | Current Month Total Deposit ≥ RM300
After WIN | Continue participating
After LOSE | Deposit RM50 required
Unlock Logic | 1 RM50 deposit unlocks 1 next participation
NOTES（备注）
Item | Description
Reward Logic | WIN reward logic has been defined separately
Campaign Period | During World Cup campaign period
Draw Option | Not available
My Predictions Prize
Achievement | Reward
Correct Prediction | 10 Tokens
2 Match Win Streak | 30 Tokens
3 Match Win Streak | 60 Tokens
4 Match Win Streak | 100 Tokens
5 Match Win Streak | 150 Tokens
6 Match Win Streak | 250 Tokens
7 Match Win Streak | 400 Tokens
8 Match Win Streak | 600 Tokens
9 Match Win Streak | 1,000 Tokens
10 Match Win Streak | 3,000 Tokens
12 Match Win Streak | Galaxy Buds3 FE
15 Match Win Streak | Vivo V30e 5G 8GB+256GB

## 3a - Avatar
Avatar
Battle Points → Level Up Avatar (Level 1 - 100)
Deposit → Get Tokens → Fight Boss → Receive Mystery Box
Concept
This is a Planet-based RPG system where players progress through Battle Points, unlock planets, fight bosses, open mystery boxes, and visually equip items on their Avatar.
Players can earn Token through:
- Deposits
- Daily & Weekly Missions
- Mini Games
- Daily Check-In
Players can earn Battle Points (BP) through: | Information
- Mini Games | Any obtain of BP will be 100x BP
- Daily & Weekly Missions
- Daily Check-In
Bottom Navigation
Menu | Description
Home | Display the player's Avatar, current Power, and equipped equipment.
Hero Item | View equipped equipment and Backpack. Players can equip or change equipment.
Universe | Challenge Bosses to earn Mystery Boxes.
Mission | Complete Daily and Weekly Missions to earn Battle Points (BP) and Tokens.
Character System
Avatar
Item | Value
Gender | Male / Female (Player can choose)
Max Level | Lv.100
Level Up Currency | Battle Points (BP)
BP Required | Current Level × 100 BP
Battle Power per Level | +500 Power
Example
Level Up | Battle Point Required
Lv.1 → Lv.2 | 100 Battle Point
Lv.2 → Lv.3 | 200 Battle Point
Lv.3 → Lv.4 | 300 Battle Point
... | ...
Lv.99 → Lv.100 | 9,900 Battle Point
Equipment System
Item | Value
Equipment Slots Available | 4
Equipment Types | Weapon, Helmet, Armor, Boots
Battle Power per Equipment | +1,000 Power
Maximum Equipment Power | 4,000 Power
Backpack | Stores spare equipment
Discard Equipment | 10 Tokens
Maximum Battle Power
Source | Battle Power
Avatar Level (Lv.100) | 50,000 BP
4 Equipped Items | 4,000 BP
Maximum Battle Power | 54,000 BP

## 3b - Challenge
Challenge
- Each Boss is tied to a specific Planet Level Requirement and drops a unique equipment type.
- Players must reach the required Power to challenge each Boss.
Planet | Boss Name | Theme | Boss Style | Power Required | HP | HP (Backend Calculation) | Remark | Equipment Reward
Starlight | Starlight Sentinel | Light | Knight | 0 | 50000 | Dice total > 6 Boss die | Damage shows doesn't matter. Important end up the boss die when the dice total has reached | Sword
Comet | Comet Reaper | Comet | Reaper | 2000 | 100000 | Dice total > 6 Boss die |  | Helmet
Meteor | Meteor Colossus | Rock & Lava | Giant | 5000 | 150000 | Dice total > 12 Boss die |  | Armor
Nebula | Nebula Warden | Cosmic | Guardian | 9000 | 200000 | Dice total > 12 Boss die |  | Shoes
Boss Battle Rules
Item | Value
Entry Requirement | Player Power ≥ Boss Power Required
Free Daily Attempt | 1
Additional Attempt Cost | 10 Tokens
Player Turn | Roll Dice → Dice Number = Number of Attacks
Boss Turn | Attacks Once (No Dice Roll)
Battle Flow | Player Roll Dice → Player attacks → Boss attacks → Repeat
Battle Result | Player Always Wins (if entry requirement is met)
Reward | 1 Mystery Box
Mystery Box Reward
No | Item | Possibility (Max = 100%) Individual Player
1 | Token x10 | 18%
2 | Token x5 | 15%
3 | Battle Points 100 | 18%
4 | Battle Points 1,000 | 8% | [6 empty] | Boss Style - sample
5 | Free Credit RM3-RM10 | 6%
6 | Token x30 | 6%
7 | Rare Equipment x1 | 6%
8 | Free Credit RM0.5-RM3 | 16%
9 | Gold Bar (0.5g) | 0%
10 | Level Up ×1 | 7%
11 | Level Up ×2 | 0%
12 | Level Up ×3 | 0%

## 3c - War
War
MRS Boss War
Deposit → Earn Attack Points → Fight Boss → Rank Up → Earn Rewards → Return Daily
Concept
Players defeat powerful world bosses while competing against each other on damage leaderboards
Users can earn Attack Points through:
Deposits
Daily Missions
Mini Games
Login Activities
Attack Points are then used to attack bosses and accumulate damage.
Higher damage equals better rankings and larger rewards.
War
| Boss Categories |  | Example Bosses
1 | Daily Boss |  | Goblin King
Fire Dragon
| Purpose: |  | Ice Titan
| Daily engagement |  | Shadow Demon
Titan Emperor
Configuration:
HP: 5,000,000
Duration: 24 Hours
Rewards: Daily Reward Pool
2 | Weekly Boss
Purpose:
Long-term competition
Configuration:
HP: 50,000,000
Duration: 7 Days
Larger Reward Pool
3 | Event Boss
Purpose:
Marketing Campaigns & Seasonal Events
Configuration:
HP: 100,000,000+
Limited Time
Exclusive Rewards
Attack System
1 | Basic Attack Logic
Every Attack Point consumed performs one attack.
Damage Range:
100 – 500 Damage
Formula:
Damage = Random(100~500)
2 | Critical Hit System
Base Critical Chance: 10%
Critical Multiplier:
2x Damage
Example:
Normal Damage: 300
Critical Damage: 600
VIP Advantage System
To encourage deposits, VIP levels receive combat advantages.
| VIP Level | Critical Rate | Damage Bonus
| VIP 0 | 10% | 1.0x
| VIP 1 | 12% | 1.1x
| VIP 3 | 15% | 1.2x
| VIP 5 | 20% | 1.5x
| VIP 8 | 25% | 2.0x
Benefits:
Faster ranking progression
Higher contribution scores
Increased competitiveness
Attack Point Economy
Free Acquisition
| Action | Attack Points
| Daily Login | 1
| Daily Check-In | 1
| Complete 3 Missions | 2
| Complete All Missions | 3
Deposit Rewards
| Deposit Amount | Attack Points
| RM30 | 2
| RM50 | 4
| RM100 | 10
| RM300 | 35
| RM500 | 70
Ranking System
Damage Leaderboard
Ranking based on:
Total Damage Contribution
Ranking Rewards
| Rank | Reward Tier
| Top 1 | Legendary Reward
| Top 10 | Epic Reward
| Top 100 | Premium Reward
| Top 1000 | Participation Bonus
| All Participants | Basic Reward
Reward System
1 | Boss Kill Rewards
Distributed after boss defeat.
Allocation based on:
Contribution Percentage
Example:
Reward Share = Personal Damage / Total Boss Damage
Ranking Rewards
Distributed after event ends.
2 | Participation Rewards
Every participant receives rewards.
Admin System
Boss Management
Admin can:
Create Boss
Edit HP
Set Duration
Configure Reward Pool
Schedule Events
Attack Configuration
Admin can configure:
Deposit → Attack Mapping
Mission Rewards
Event Multipliers
Damage Configuration
Admin controls:
Minimum Damage
Maximum Damage
Critical Rate
VIP Bonuses
Reward Configuration
Admin controls:
Ranking Rewards
Participation Rewards
Kill Rewards
Seasonal Rewards

## 3d - Mission
Rename Avatar Missions
Daily Mission
Mission | Requirement | Reward
Daily Login | Login 1 day | 100 BP
Boss Challenger | Complete 1 Boss Battle | 200 BP
Daily Deposit | Deposit RM100 | 300 BP +2 Token
Daily Completion | Complete 3 Missions | 500 BP
Weekly Mission |  |  | Missions
Mission | Requirement | Reward | Every RM100 Deposit earns 10 Tokens (10 Tokens = 1 Boss Challenge)
Weekly Deposit | Deposit RM500 | 2,000 BP +5 Token | Complete tasks to earn extra Tokens & Battle Points
Boss Hunter | Complete 10 Boss Battle | 3,000 BP
Equipment Collector | Obtain 1 Equipment | 1,000 BP
Weekly Active | Login 5 days | 2,000 BP
Monthly Mission
Mission | Requirement | Reward
Monthly Deposit | Deposit RM3,000 | 10,000 BP +20 Token
Boss Master | Complete 30 Boss Battle | 10,000 BP
Monthly Active | Login 20 days | 10,000 BP
Achievement
Mission | Requirement | Reward
Full Equipment Set | Collect all 4 Equipment | 5,000 BP +10 Token

## P2A - Penalty Kick (hidden)
No | Reward Name | Quantity | Item Type | Image | Action
1 | xxxx | xx | xxxx | x | Edit / Archieve
Buttons
Action (Edit / Archive)
1 | When click to edit button, allow admin update the details below
Fields 1. Reward Name 2. Quantity 3. Unlimited (Tick Box) 4. Item Type - Free credit - Min withdraw - Max withdraw - Token - Prize - Worldcup leaderboard score 5. Image
2 | When click to Archive button, allow admin archive the selected reward
Create new reward
1 | At top right side, will have a button called "Create new reward"
2 | When click to the button, allow admin create new reward
Fields 1. Reward Name 2. Quantity 3. Unlimited (Tick Box) 4. Item Type - Free credit - Min withdraw - Max withdraw - Token - Prize - Worldcup leaderboard score 5. Image
Kick Sequence
1 | At top right side, will have a button called "Kick Sequence setting"
2 | When click to the button, allow admin setting sequence
Fields 1. Position 2. Reward selection
Game Status
1 | Beside Kick Sequence setting, will have a button called "Game Status"
2 | When click to the button, allow admin setting Game Status
Fields 1. Open / Close 2. Maintenance Mode
Cost Setting
1 | Beside Game Status setting, will have a button called "Cost Setting"
2 | When click to the button, allow admin setting Cost Setting
Fields 1. Cost per kick (token?/kick)
Goalkeeper Difficulty
1 | Beside Cost setting, will have a button called "Goalkeeper Difficulty"
2 | When click to the button, allow admin setting Goalkeeper Difficulty
Fields 1. Easy (75%) 2. Medium (50%) 3. Hard (25%)
Reward

## P2A - Mission (hidden)
No | Mission Name | Category | Description | Mission Type | Reset Type | Condition Builder | Reward | Limit Control | Action
1 | xxxx |  | xxxx | [5 empty] | Edit / Archieve
Buttons
Action (Edit / Archive)
1 | When click to edit button, allow admin update the details below
Fields 1. Mission Name 2. Mission Category - Daily mission - Weekly mission - Challenge mission 3. Description (Member view) 4. Mission Type - One time - Repeatable - Recurring 5. Reset Type - Daily - Weekly - Monthly - None 6.Condition Builder a. Action - Login - Deposit Amount - Play Spin - Play Smash - Check in - Play Kick - Withdraw Amount - Referral friend - Redemption b. Time Based c. Accumilate 7. Reward a. Token quantity 8. Limit Control
2 | When click to Archive button, allow admin archive the selected mission
Create new mission
1 | At top right side, will have a button called "Create new mission"
2 | When click to the button, allow admin create new mission
Fields 1. Mission Name 2. Mission Category - Daily mission - Weekly mission - Challenge mission 3. Description (Member view) 4. Mission Type - One time - Repeatable - Recurring 5. Reset Type - Daily - Weekly - Monthly - None 6.Condition Builder a. Action - Login - Deposit Amount - Play Spin - Play Smash - Check in - Play Kick - Withdraw Amount - Referral friend - Redemption b. Time Based c. Accumilate 7. Reward a. Token quantity 8. Limit Control

## P2A - World Cup Leaderboard Sys (hidden)
No | Banner title | Banner subtitle | Label text | Description | Image | Action
1 | xxxx |  |  |  |  | Edit / Save
Buttons
Action (Edit / Save)
1 | When click to edit button, allow admin update the details below
| Fields 1. Information (Text Box) 2. Terms and Condition (Text Box) | [5 empty] | 1. Banner title (Text Box) 2. Banner subtitle (Text Box) 3. Label text (Text box) 4. Description 5. Image

## Sheet20 (hidden)
No | Reward Name | Quantity | Item Type | Image | Description | Country | Action
1 | xxxx | xx | xxxx | x | xxx | xxx | Edit / Archieve
Buttons
Action (Edit / Archive)
1 | When click to edit button, allow admin update the details below
Fields 1. Reward Name 2. Quantity 3. Item Type - Prediction - Top Country - Global Top Player 4. Image 5. Description 6. Country
2 | When click to Archive button, allow admin archive the selected reward
Create new reward
1 | At top right side, will have a button called "Create new reward"
2 | When click to the button, allow admin create new reward
Fields 1. Reward Name 2. Quantity 3. Item Type 4. Image 5. Description 6. Country

## Sheet21 (hidden)
No | Country | Rank | Player Name | Total Points | Action
1 | xxxx | xx | xxxx | x | Edit / Archieve
Buttons
Action (Edit / Archive)
1 | When click to edit button, allow admin update the details below
Fields 1. Country 2. Rank 3. Player 4. Total Points
2 | When click to Archive button, allow admin archive the selected data
Create new data
1 | At top right side, will have a button called "Create new data"
2 | When click to the button, allow admin create new data
Fields 1. Country 2. Rank 3. Player 4. Total Points

## P2B - Smash Egg (hidden)
No | Reward Name | Quantity | Item Type | Image | Action
1 | xxxx | xx | xxxx | x | Edit / Archieve
Buttons
Action (Edit / Archive)
1 | When click to edit button, allow admin update the details below
Fields 1. Reward Name 2. Quantity 3. Unlimited (Tick Box) 4. Item Type - Free credit - Min withdraw - Max withdraw - Token - Prize 5. Image
2 | When click to Archive button, allow admin archive the selected reward
Create new reward
1 | At top right side, will have a button called "Create new reward"
2 | When click to the button, allow admin create new reward
Fields 1. Reward Name 2. Quantity 3. Unlimited (Tick Box) 4. Item Type - Free credit - Min withdraw - Max withdraw - Token - Prize 5. Image
Smash Sequence
1 | At top right side, will have a button called "Smash Sequence setting"
2 | When click to the button, allow admin setting sequence
Fields 1. Position 2. Reward selection

## P2B - Top 20 Deposit Leaderboar (hidden)
No | Information | Action
1 | xxxx | Edit / Save
No | Terms and Condition | Action
1 | xxxx | Edit / Save
Buttons
Action (Edit / Save)
1 | When click to edit button, allow admin update the details below
Fields 1. Information (Text Box) 2. Terms and Condition (Text Box)

## Glossary (hidden)
Glossary
No | Title | Description
1 | Member
2 | Token
3 | Date Format | DD / MM / YYYY
4 | Date Time Format | DD / MM / YYYY HH:MM:AM/PM

## Old Pages (hidden)
Frontend |  |  | BackOffice
No | Page | Details to have | No | Page | Details to have
Phase 1
1 | Home | - Member details(current rank, gap to new rank) - Lucky Spin Page - Pop-Up Notification | 1 | Home Dashboard | - Member activity overview - Daily check-in summary - Total active users
2 | Lucky Spin | - Lucky Spin (Spin Wheel) - Live winner list - Wining Record (Player) - Prize List - Spin Now Button - Spin Button with combo set - Tnc | 2 | Lucky Spin Management | - Set sequence for lucky spin
3 | Daily check-in | - Seven days (Weekly) - Progress Bar - Special day check in (EXP: 3rd day can get x2 points) - Check in Record - Tnc | 3 | Daily check-in | - Set check in items - Set Special Check in items - Tnc text field
4 | Points Redemption Mall | To allow Customers to view Gift List and Points to Redeem For Reference : https://mbi8myr.com/ - Gift - Bonus - Mini Game Lucky Spin Token | 4 | Points Redemption Mall | - Manage gift catalog - Set point cost per item - Stock control - Redemption logs - Redemption list with approval
5 | VIP membership | - Current rank , gap to new rank - Monthly Bonus (Have button to claim) - Weekly Bonus (Have button to claim) - Birthday Bonus (Have button to claim) - Tier Upgrade Bonus (Have Button to claim) - VIP Rank Detail & TnC | 5 | VIP Membership Panel | - Define VIP tiers - Set requirements per tier (turnover, deposit) - VIP activity logs
6 | Profile | - Purchase / Redeem History | 6
|  |  | 7 | Reports | - Daily/weekly active users - Redemption summary
|  |  | 8 | User Management | - Create/edit backend admin accounts - Assign roles & permissions (e.g., Super Admin, Moderator, Viewer) - Enable/disable admin access - Login activity logs (IP, time, status) - Password reset - Audit trail - Role - based access control
Phase 2 |  |  | Phase 2
1 | Smash Egg Jackpot | - Set 3 Jackpot Bar - Set 9 pieces Egg icon - Set share button Grand Jackpot = 888 Major Jackpot = 188 Mini Jackpot = 88 Consolation Prize = 8 Smash 3 Egg with same pattern to get related Jackpot Smash 3 Egg with different pattern to get Consolation Prize For Reference : https://cekap33reward.com/?userId= | 1 | Smash Egg Jackpot | - Control prize pool & probability - Set 3 Smash Egg daily limits
2
3
Phase 3

## Appendix (hidden)
No | Description | Details | Remark
1 | Website Reference
2 | Logo
3 | Button
4 | Symbolic Icons
5 | Membership Design | https://dribbble.com/shots/20049577-Membership-Tiered-Loyalty-Program
6 | Game - Lucky Spin | Image 1 [G5] MRS - Project Details
7 | Mission | Image 2 [G5] MRS - Project Details
8 | Banner Carousel | Image 3 [G5] MRS - Project Details
9 | Video | Image 4 [G5] MRS - Project Details
10 | Redeemption Reward | Image 5 [G5] MRS - Project Details
11 | Game - Girl